## Sheet1
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%

## October
October: Week 1-4 - Initial Setup and Core Features
Week | Tasks | Goal
Week 1 (Oct 1-4) | Set up Django project and SDV generator app. | Set up a basic Django project and create the app. Install necessary dependencies, configure basic settings.
Install dependencies (openpyxl).
Configure project settings and database in order to test with the sample data
Week 2 (Oct 7-11) | Design the Metadata model with fields (name, description, file). | Build and test core functionality for handling file uploads and parsing Excel files. Set up the admin interface.
Register Metadata model in admin.
Run migrations.
Create ExcelUploadForm and set up URL routing.
Week 3 (Oct 14-18) | Create upload_excel.html for the upload form. | Create the file upload form, handle file uploads, parse Excel files, and render data in a simple table.
Implement upload_excel view and Excel file parsing logic using openpyxl. Trying to develop a deaunthetication login feature in SDV tool's UI (Still in progress)
Test file upload and data parsing.
Week 4 (Oct 21-31) | Create show_excel.html to display the parsed Excel data. | Complete the file upload functionality, display data, and finalize the admin panel. Add error handling for uploads.
Test displaying data on the web page.
Add error handling for file uploads.
Enhance the admin interface with list_display and search_fields.(Still under development in order to enhance the UI)

## November
November: Week 5-8 - Advanced Features and Enhancements
Week | Tasks | Goal
Week 5 (Nov 1-8) | Implement Excel export functionality. | Add features to export data to Excel and paginate large datasets. Enhance the admin interface with filtering options.
Add pagination for large datasets in the show_excel.html page.(Still in progress sometimes it doesn't upload properly)
Implement filtering in the admin panel.
Week 6 (Nov 11-15) | Add search functionality in show_excel.html. | Improve the front-end by adding search, implement user authentication and role management for access control.
Implement user authentication (login/logout).
Create user roles for restricting access (admin, viewer).
Week 7 (Nov 18-22) | Write tests for the views, forms, and models (file upload, parsing). | Write and run unit tests for various app features. Ensure export and pagination work correctly.
Test the export functionality and pagination.
Finalize error handling for user input.
Week 8 (Nov 25-29) | Set up the app to run in server environment. | Ensure the app is ready for deployment. Test it in a production-like environment, finalize bug fixes.
Test deployment in a staging environment (locally or via a staging server).
Final round of bug fixing.(since large datasets are in still progress still this phase is not yet completed)

## December
December: Week 9-12 - Finalization and Deployment
Week | Tasks | Goal
Week 9 (Dec 2-6) | Implement background tasks | Set up background tasks (optional) and improve UI. Add admin/editor roles for restricting access to features.
Add user roles for admin and editor functionality.
Enhance the UI with better styling (use Bootstrap).
Week 10 (Dec 9-13) | Final testing and bug fixing. | Finalize testing, bug fixing, and documentation. Ensure everything is working smoothly before deployment.
Create final documentation for using the app (uploading, exporting, searching).
Write final unit tests.
Week 11 (Dec 16-20) | Deploy the project to real-time workspace | Deploy the application to a live environment and test everything thoroughly. Set up monitoring (optional).
Test the live environment.
Set up error tracking while using real-time datas
Week 12 (Dec 23-27) | Final round of bug fixing and optimization. | Ensure everything works in production, finalize optimizations, and prepare the app for the final review/presentation.
Conduct final review of the codebase as well as trying to implement large set of synthetic data that have to store it in a database in order to fetch them directly instead of uploading
Prepare for Final review